## User story
Issue Type | Summary | Priority
Epic 1 | Comprehensive Management of Corporate Entities
Story 1 | User wants to quickly locate specific company records using global keywords and dynamic filters. | High
Sub story 1 | Validate global keyword search results for Quantum FinTech Solutions
Sub story 2 | Test filter panel visibility and default view reset functionality
Story 2 | User wants to ensure company data accuracy and seamless navigation within the interactive grid | High
Sub story 1 | Verify address column accuracy and record detail link navigation
Sub story 2 | Check row count synchronization during data grid pagination cycles
Story 3 | User wants to easily access entry points for creating, editing, and viewing company records | High
Sub story 1 | Confirm successful routing to the company creation form page
Sub story 2 | Verify functionality of inline edit and delete action buttons
Story 4 | User wants to perform administrative actions on multiple company records simultaneously for better efficiency | Medium
Sub story 1 | Test select-all checkbox logic and footer action menu state
Sub story 2 | Validate bulk user assignment for multiple selected company records

## Test Scenarios
TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
TS_001 | ST_01 | Validate effectiveness of global search and filtered data views. | Functional / UI | 4 | 1. Validate that entering "Quantum" in search returns the correct company record. 2. Verify that clicking "Show Filters" button displays the hidden filtering panel. 3. Check that "Default View" resets all applied search filter criteria successfully. 4. Ensure searching invalid strings displays the "No records found" feedback message.
TS_002 | ST_02 | Verify company information accuracy and data grid navigation. | Data Integrity | 3 | 1. Validate that the company address column displays the full concatenated location details. 2. Verify that clicking the company name hyperlink successfully redirects to the record. 3. Confirm that the pagination footer correctly reflects the total record count after deletion.
TS_003 | ST_03 | Validate navigation triggers for creating and modifying company records. | Smoke / UI | 4 | 1. Validate clicking "Create" button opens the new company entry form. 2. Verify inline "Edit" button opens the record modification interface correctly. 3. Ensure "View" icon opens the non-editable record summary details page. 4. Confirm clicking "Cancel" in the form returns to the company grid.
TS_004 | ST_03 | Verify execution of multi-record selection and bulk operations. | Functional / Regression | 4 | 1. Validate that the header checkbox selects all visible records in grid. 2. Verify "Actions" dropdown enables only when records are currently selected. 3. Check that "Bulk Delete" action successfully removes all selected company records. 4. Confirm "Assign to User" bulk action updates multiple record owners correctly.

## Test cases
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
TC_001 | TS_001 | User is logged in and the Companies grid is displayed | Validate that searching "Quantum" returns the specific company record | 1. Click Search field 2. Type "Quantum" 3. Press Enter | Quantum | Grid should display only Quantum FinTech Solutions | Grid filtered correctly to show Quantum record | Passed |  |  | Validates positive search | ST_01
TC_002 | TS_001 | User is on the Companies page with the grid loaded | Validate that clicking "Show Filters" button displays the hidden panel | 1. Locate "Show Filters" button 2. Click the button |  | The filtering UI panel should expand above the grid | Filtering panel became visible upon clicking button | Passed |  |  | Tests UI toggle logic | ST_01
TC_003 | TS_001 | A search or filter has been actively applied to grid | Check that "Default View" resets all applied search filter criteria | 1. Click View dropdown 2. Select "Default View" |  | Grid should reset to show all company records. | All filters cleared and full list displayed | Passed |  |  | Tests state reset | ST_01
TC_004 | TS_001 | User is logged in and the Companies grid is displayed | Ensure searching invalid strings displays the "No records found" message | 1. Click Search field 2. Enter random string 3. Press Enter | XYZ_999 | Grid should show a message: "No records found." | "No records found" displayed as expected | Passed |  |  | Negative test case | ST_01
TC_005 | TS_002 | Companies list contains records with multi-line address data | Validate that address column displays full concatenated location details correctly | 1. Observe the Address column for Quantum record |  | Address should show Street, City, State, and PIN | Full address string displayed without truncation | Passed |  |  | Data integrity check | ST_02
TC_006 | TS_002 | The Companies data grid is populated with active records | Verify that clicking company name hyperlink successfully redirects to record | 1. Hover over company name 2. Click the link |  | Browser should navigate to the detailed company view | Successfully navigated to the record detail page | Passed |  |  | Navigation test | ST_02
TC_007 | TS_002 | Multiple company records exist to trigger the pagination footer | Confirm that pagination footer correctly reflects total record count changes | 1. View footer label 2. Delete one record 3. Check label |  | The "Showing X records" count should decrease by one | Count updated from "1 records" to "0 records." | Passed |  |  | Logic validation | ST_02
TC_008 | TS_003 | User is on the main Companies dashboard view | Validate clicking "Create" button opens the new company entry form | 1. Locate "Create" button 2. Click the button |  | The "Create New Company" form should load successfully | Redirected to /companies/new form page | Passed |  |  | Smoke test | ST_03
TC_009 | TS_003 | At least one company record exists in the data grid | Verify inline "Edit" button opens the record modification interface | 1. Locate Edit icon in row 2. Click Edit icon |  | The Edit form with pre-filled data should open | Form opened with editable Quantum FinTech data | Passed |  |  | Functional test | ST_03
TC_010 | TS_003 | At least one company record exists in the data grid | Ensure "View" icon opens the non-editable record summary page | 1. Click "Unhide" (Eye) icon 2. Observe page fields |  | Summary page should open in a read-only state | Record displayed in read-only summary view | Passed |  |  | Permission test | ST_03
TC_011 | TS_003 | User is currently on the "Create New Company" form | Confirm clicking "Cancel" in form returns to company grid | 1. Click Cancel button 2. Observe the URL |  | System should return to the main Companies grid | Returned to /companies view without saving | Passed |  |  | Navigation test | ST_03
TC_012 | TS_004 | Multiple records are displayed in the company data grid | Validate that header checkbox selects all visible records in grid | 1. Click checkbox in header 2. Check all row boxes |  | Every row in the grid should be checked | All rows were selected with one click | Passed |  |  | Bulk UI test | ST_04
TC_013 | TS_004 | No records are currently selected in the data grid | Verify "Actions" dropdown enables only when records are selected | 1. View Actions dropdown 2. Select a row 3. Re-view dropdown |  | Dropdown should be disabled until a row is picked | Dropdown menu is clickable and options are visible even with 0 rows selected | Failed |  |  | UI Logic Bug: The disabled attribute is missing from the dropdown trigger | ST_04
TC_014 | TS_004 | Two or more company records are selected for deletion | Check that "Bulk Delete" action successfully removes all selected records | 1. Select two records 2. Select Delete in Actions 3. Click Checkmark |  | Selected records should disappear from the data grid | Selected company records were successfully removed from the database and grid | Passed |  |  | Bulk UI test | ST_04
TC_015 | TS_004 | One or more company records are selected for assignment | Confirm "Assign to User" bulk action updates record owners correctly | 1. Select record 2. Select "Assign to user" 3. Click Checkmark | User: Snehal | The "Assigned To" field should update to Snehal | Record owner changed in UI, but the original creator still has full edit access | Failed |  |  | Security/Permission Bug: The creator still has full edit access | ST_04

## Defect Report
Defect Id. | Module name | Defect Summary | Defect Priority | Assigned To | Status
DEF_001 | Companies / Grid UI | "Actions" dropdown is active and clickable before any company record is selected. | Medium | snehalghosh22@gmail.com | To do
DEF_002 | Companies / Permissions | Assigned record remains fully accessible (Edit/Delete) to the original creator after transfer. | High | snehalghosh22@gmail.com | To do

## RTM
BR_ID | TR_ID | TS_ID | TC_ID | STATUS | DR_ID
BR_01 | TR_COMP_01 | TS_001 | TC_001 | Passed
BR_01 | TR_COMP_01 | TS_001 | TC_002 | Passed
BR_01 | TR_COMP_01 | TS_001 | TC_003 | Passed
BR_01 | TR_COMP_01 | TS_001 | TC_004 | Passed
BR_02 | TR_GRID_02 | TS_002 | TC_005 | Passed
BR_02 | TR_GRID_02 | TS_002 | TC_006 | Passed
BR_02 | TR_GRID_02 | TS_002 | TC_007 | Passed
BR_03 | TR_CRUD_03 | TS_003 | TC_008 | Passed
BR_03 | TR_CRUD_03 | TS_003 | TC_009 | Passed
BR_03 | TR_CRUD_03 | TS_003 | TC_010 | Passed
BR_03 | TR_CRUD_03 | TS_003 | TC_011 | Passed
BR_04 | TR_BULK_04 | TS_004 | TC_012 | Passed
BR_04 | TR_BULK_04 | TS_004 | TC_013 | Failed | DEF_001
BR_04 | TR_BULK_04 | TS_004 | TC_014 | Passed
BR_04 | TR_BULK_04 | TS_004 | TC_015 | Failed | DEF_002

## Summary
TEST EXECUTION SUMMARY
Project Name | Module Name | Total Cases | Total Passed | Total Failed | Total Executed | Pass Percentage | Fail Percentage | Completion Percentage
Free CRM | Companies Management Module | 15 | 13 | 2 | 15 | 86.67% | 13.33% | 100%
| Sign Up | 2 | 2 | 0 | 2 |  | 0% | 100%